## Sheet1
Project Details | Start Date | End Date
Requirements document draft and phase 1 check in | 2021-06-09 | 2021-06-16
Client meeting | 2021-06-21 | 2021-06-21
Updated Requirements and design document | 2021-06-21 | 2021-06-22
Schedule document | 2021-06-23 | 2021-06-23
Phase 2 check in |  | 2021-06-23